# SD 5-Year State Plan to Support Struggling Readers, including Students with Dyslexia

# Summary of Progress

# Identification of Students with Dyslexia

- Pursue a plan to use Response to Intervention (RtI) to determine eligibility

- 2017: The Department of Education (DOE) brought together a stakeholder group to investigate other states’ processes and resources to better understand how to use the RtI process for determining Specific Learning Disability (SLD) eligibility.

- 2017: Attended the Nebraska MTSS conference in August 2017 to learn more about using the RtI process for SLD eligibility.

- 2017: Connected with Mark Shinn during the conference and contracted with him to come to SD and work with our MTSS team to develop a plan for using the RtI process to help ensure the best interventions are being used at each level for struggling readers.

- 2019:

- A workgroup met in Pierre on April 1 to discuss the necessary changes to the current Multi-tiered Systems of Support (MTSS) manual to include using RtI for eligibility purposes.  The group will meet back in September to finalize the document.

- Support schools in using screeners to identify students with characteristics of dyslexia

- 2018-2019: DOE is working with the South Dakota Association of School Psychologists and the Oregon Department of Education to identify valid and reliable screeners.  A list is posted on the SD dyslexia webpage.

- Work with South Dakota Association of School Psychologists to ensure local evaluation teams have the knowledge and capacity to evaluate and diagnose dyslexia

- 2019:  Three trainings are planned for October and November of 2019 with Dr. Kari Oyen and Dr. Daniel Hajovsky.  These trainings are open to all SD districts and require the district to send a team of at least two people.  These trainings will also include consultation to the teams after the training.

# Guidance & Supports

- Provide districts with information and resources/tools to support students with dyslexia as a learning disability

- 2016-17: A workgroup of stakeholders, including parents, was established to review the state’s dyslexia handbook and an informational flyer. The updated versions of the handbook and other resources are posted on DOE’s website.  A press release was issued in August and shared with all district administrators and other educator email listservs.

- 2017: DOE partnered with Marsha Weiland from Decoding Dyslexia to conduct a webinar focused on dyslexia for district curriculum directors and administrators.

- 2017-18: DOE highlighted October as Dyslexia Awareness Month by sharing resources and information via Thursday Tidbits, a newsletter for reading/language arts teachers; special education director calls and special education monthly newsletters.

- 2019: Continue to update DOE dyslexia webpage resources and send out information on listservs and in DOE newsletters.

2. Offer series of professional learning opportunities

2a:  Series of online workshop opportunities

- 2018: DOE has started to identify existing online workshops that could be offered to districts.

- 2019: Previewed an online training program and have put together a team to further review, waiting on vendor to provide access as of July 2019.

2b:  Face-to-face dyslexia workshop

- 2017: DOE partnered with the SD Speech-Language-Hearing Association (SDSLHA) and the International Dyslexia Association – Upper Midwest Branch to conduct a dyslexia training called “Literacy for All – Understanding Language, Learning and Dyslexia.” It was held Oct. 4, 2017, as a pre-session to the State Speech Language Pathologists (SLP) conference. It was open to anyone. The cost to DOE was approximately $8,000.

- 2018: DOE is partnering with the SD Speech-Language-Hearing Association (SDSLHA) to offer a pre-conference session on dyslexia in Oct. 2018

2c:  MTSS (Multi-tiered System of Support) Summer Conference focusing on struggling readers

- 2017:  More than 350 educators attended the MTSS Summer Conference in June 2017. Sessions focused on support for schools implementing MTSS and included information about working with students with dyslexia. The 2018 conference is scheduled for June 20-21.

- 2018:  The 2018 MTSS Summer Conference was held June 20-21.  June 20 featured Kristin R. Anderson with Visible Learning.  Kristin is an associate of John Hatti and presented on his work focusing on strategies to produce the best results for students.  225 educators attended this session.

- 2019:  The MTSS Summer Conference was held on June 11 & 12.  The 95% group provided training that included interventions for students with learning disabilities.  250 educators attended.

2d:  Foundational reading training

- 2017:  Two-part foundational reading trainings were held in July and August 2017 to support K-3 educators (48 participants) and 4-8 educators (42 participants).

- 2018:  Two-part foundational reading trainings were held in July and August 2018 to support K-3 educators (60 participants) and 4-8 educators (60 participants). This year the class size was expanded to accommodate interest in the course and waitlist numbers.

- 2019:  Foundational Reading Skills training for K-3 grade teachers will be held on July 1, 2019.  Training for grades 4-8 will be held on July 30, 2019.

3.  Develop a program focused on structured literacy including professional development for K-5 classroom and special education teachers

- 2017-2019: DOE was awarded a five-year grant from the federal Office of Special Education Programs.  The goal of this South Dakota State Personnel Development Grant (SD SPDG) is to develop a systematic, cohesive, collaborative and sustainable evidence-based literacy model that uses data and engages families and can be implemented with any district needing support for struggling readers, especially students with specific learning disabilities (SLD). The expected outcome of the proposal is to develop and align a professional learning and development (PLD) system that provides special education and general educators with the knowledge and skills to provide access and instruction to students with SLDs so that their proficiency in literacy increases.

- Partners include IHE – DSU, and Parent Connections

- Additional information regarding the SD SPDG grant is found on the following website:  https://doe.sd.gov/grants/SPDG.aspx

# Connections with Postsecondary

- Work with university programs to ensure structured literacy and dyslexia are taught in elementary education, special education and reading endorsement programs

- 2018: DOE has begun conversations with a university professor to work with other universities  to identify coursework where structured literacy and dyslexia are currently taught and identify workgroup members to develop guidelines.

- Add a literacy interventionist certification

- 2019: On hold due to staffing-, DOE plans to gather information on other states’ certification requirements for a literacy interventionist with the goal of creating certification rules.

3.  Work with the universities to ensure DOE professional learning opportunities will meet the requirements for university reading endorsement programs

- 2019: DOE has partnered with Dakota State University to offer credit for the training offered through the SD SPDG grant.   DOE will work with the DSU professor to review the SPDG credit for alignment with  the university reading endorsement.