FIVE YEAR STATE COMMITMENT TO PROFESSIONAL DEVELOPMENT AND DISTRICT RESPONSIBILITY PLAN FOR

MTSS IMPLEMENTATION BEGINNING WITH RtI K-3

| MTSS Year 1 Year 1 (RtI) | Summer -Building principal attends principal training (1 day in PIerre) -RtI building team attends regional MTSS(RTI) Trainings: 1.Big picture overview 2. create action plan 3. scheduling all events and trainings for year 1 (3 days) | Summer -Train all teachers to administer the screener. (DIBELS, AIMSweb) (2 days regional sites) | Prior to fall in service -RtI building team will meet with state MTSS coordinator to finalize the action plan and prepare presentation for fall in service for all staff (1/2 day) | Fall in service -Overview of RTI to all building staff MTSS/RTI. (3 hours) | Fall/Winter/Spr -Universal screener given 3 times per year (first 2 weeks of school, 2 weeks immediately prior to Christmas break, final 2 weeks of school year). Data will be shared with MTSS coordinator and SD-STARS. | Year Round -Analyze universal screening data following the procedure outlined in the SD MTSS Data Workbook for Reading following each benchmark period. MTSS (RTI) team will meet with MTSS coordinator once per month to monitor the fidelity of implementation of action plan. | Year Round -Core Sourcebook reading instruction for all instructional staff. (5 days of PD scheduled throughout the year) | DOE will provide coordinator NOTE: User name and password will be provided to state MTSS coordinator enabling access to all student level data) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MTSS Year 2 Year 2 (RtI) | August -Train all new teachers to administer the screener. (DIBELS, AIMSweb) (2 days, regional sites) | Fall/Winter/Spr -Universal screener given 3 times per year (first 2 weeks of school, 2 weeks immediately prior to Christmas break, final 2 weeks of school year). Data will be shared with MTSS coordinator and SD-STARS. | Fall/Winter/Spr -Analyze universal screening data following the procedure outlined in the SD MTSS Data Workbook for Reading following each benchmark period. | Year Round -Continue to strengthen Tier 1 instruction -Core Sourcebook reading instruction for all new instructional staff. | Year Round -All school staff will implement Tier II, and III interventions. | After Fall Benchmark -Begin Progress monitoring all students receiving Tier II and III interventions | During School Year -MTSS (RTI) team will meet with MTSS coordinator once per month to monitor the fidelity of implementation of action plan. | DOE will provide coordinator NOTE: User name and password will be provided to state MTSS coordinator enabling access to all student level data) | Consider implementation at secondary level. |

| MTSS Year 3 Year 3 (RtI) Year 1 (PBIS) | August -Train all new teachers to administer screening tool. (2 days, regional sites) Summer -Principals attend principal training (1 day) -PBIS building team attends training to develop action plan for tier 1 (3 days) | Fall/Winter/Spr -Universal screener given 3 times per year (first 2 weeks of school, 2 weeks immediately prior to Christmas break, final 2 weeks of school year). Data will be shared with SD-STARS. Prior to Fall In- service -PBIS building team will meet with state MTSS coordinator to finalize the action plan and prepare presentation for fall in service for all staff (1/2 day) | Year Round -All school staff will implement Tier II, and III interventions. Fall In-service -Overview of PBIS to all building staff. (3 hours) | Year Round -Continue to strengthen Tier 1 instruction -Core Sourcebook reading instruction for all new instructional staff. Year Round -Analyze behavioral data following the procedure outlined in the SD MTSS Data Workbook for Behavior - MTSS (PBIS) team will meet with MTSS coordinator every other month to monitor the fidelity of implementation of action plan. | After Fall Benchmark -Continue progress monitoring all students receiving Tier II and III interventions. Fall/Winter/Spr - Complete the online self assessment Team Implementation Checklist (TIC) | MTSS (RTI) team will meet with MTSS coordinator 1-4 times per year to monitor the fidelity of implementation of action plan. Fall and Spring -PBIS coaches will attend one coaches’ training in the fall and one in the spring. Regional DDN sites will be made available in Rapid City, Aberdeen, Chamberlain, and Todd County | *Consider implementation at secondary level. Winter/Spring Work with MTSS evaluator to have an onsite evaluation and have staff, parents, and students complete the MTSS survey |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MTSS Year 4 Year 4( RtI) Year 2 (PBIS) | August Train all new teachers to administer screening tool Summer -Attend 1 day PBIS booster training as a building level team to review data and make adjustments to action plan and look at tier 2 and 3 interventions | Universal screener given 3 times per year (first 2 weeks of school, 2 weeks immediately prior to Christmas break, final 2 weeks of school year). Data will be shared with SD-STARS. Prior to Fall In- service -PBIS building team will meet with state MTSS coordinator to finalize the action plan and prepare presentation for fall in service for all staff (1/2 day) | Continue Tier II, and III interventions. Fall In-service -Provide updates to school staff. (1-2 hours) | Continue to strengthen Tier 1 instruction Core Sourcebook reading instruction for all new instructional staff. (5 days of PD scheduled throughout the year) Year Round -Analyze behavioral data following the procedure outlined in the SD MTSS Data Workbook for Behavior - MTSS (PBIS) team will meet with MTSS coordinator every other month to monitor the fidelity of implementation of action plan. | Continue to Progress monitoring all students receiving Tier II and III interventions. Fall/Winter/Spr - Complete the online self assessment Team Implementation Checklist (TIC) | MTSS (RTI) team will meet with MTSS coordinator 1-4 times per year to monitor the fidelity of implementation of action plan. Fall and Spring -PBIS coaches will attend one coaches’ training in the fall and one in the spring. Regional DDN sites will be made available in Rapid City, Aberdeen, Chamberlain, and Todd County | Winter/Spring Work with MTSS evaluator to have an onsite evaluation (School-wide Evaluation Tool SET) and have staff, parents, and students complete the MTSS survey |
| MTSS Year 5 Year 3 (PBIS) | Summer -Attend 1 day PBIS booster training as a building level team to review data and make adjustments to action plan. Add tier 2 and 3 interventions to action plan | Prior to Fall In- service -PBIS building team will meet with state MTSS coordinator to finalize tier 2 and tier 3 interventions in action plan and prepare presentation for fall in service for all staff (1/2 day) | Fall In-service -Provide updates and tier 2 and 3 interventions to school staff. (1-2 hours) | Year Round -Analyze behavioral data following the procedure outlined in the SD MTSS Data Workbook for Behavior - MTSS (PBIS) team will meet with MTSS coordinator as needed to ensure the fidelity of implementation of action plan. | Fall/Winter/Spr - Complete the online self assessment Team Implementation Checklist (TIC) | Fall and Spring -PBIS coaches will attend one coaches’ training in the fall and one in the spring. Regional DDN sites will be made available in Rapid City, Aberdeen, Chamberlain, and Todd County | Winter/Spring Work with MTSS evaluator to have an onsite evaluation(School-wide Evaluation Tool SET) and have staff, parents, and students complete the MTSS survey |